## Sheet1
Controller | Region | Owner | StartDate | EndDate | Hours | Owner | StartDate | EndDate | Hours
AdminControllerRegister | Notifications | Deepshikha | 2021-03-25 | 2021-03-26 | 5 | Pawan | 2021-03-26 | 2021-03-26 | 6
AdminControllerRegister | Reset Login Password | Deepshikha | 2021-03-26 | 2021-03-30 | 5 | Pawan | 2021-03-26 | 2021-03-30 | 5
AdminControllerMaster | Change Password | Deepshikha | 2021-03-30 | 2021-03-30 | 5 | Pawan | 2021-03-30 | 2021-03-30 | 5
AdminControllerMaster | Unblock User | Deepshikha | 2021-03-31 | 2021-03-31 | 5 | Pawan | 2021-03-31 | 2021-03-31 | 6
AdminControllerMaster | Post Mater | Deepshikha | 2021-04-01 | 2021-04-01 | 4 | Pawan | 2021-04-01 | 2021-04-01 | 6
AdminControllerMaster | Department Mater | Deepshikha | 2021-04-05 | 2021-04-05 | 4 | Pawan | 2021-04-05 | 2021-04-05 | 6
AdminController | Division Mater | Deepshikha | 2021-04-06 | 2021-04-06 | 4 | Pawan | 2021-04-06 | 2021-04-06 | 6
SharedController | Site Master | Deepshikha | 2021-04-07 | 2021-04-07 | 6 | Pawan | 2021-04-07 | 2021-04-07 | 6
UploadController | Register | Deepshikha | 2021-04-08 | 2021-04-08 | 6 | Pawan | 2021-04-08 | 2021-04-08 | 6
AdminController | EmployeeUpload | Deepshikha | 2021-04-09 | 2021-04-09 | 6 | Pawan | 2021-04-09 | 2021-04-09 | 6
Team | Auto Login Creation | Deepshikha | 2021-04-12 | 2021-04-12 | 6 | Pawan | 2021-04-12 | 2021-04-12 | 6
AdminControllerRegister | Team Master | Deepshikha | 2021-04-13 | 2021-04-13 | 6 | Pawan | 2021-04-13 | 2021-04-13 | 6
AdminControllerRegister | Register | Deepshikha | 2021-04-14 | 2021-04-14 | 6 | Pawan | 2021-04-14 | 2021-04-14 | 6
AdminControllerMaster | Employee Data Update | Deepshikha | 2021-04-15 | 2021-04-15 | 6 | Pawan | 2021-04-15 | 2021-04-15 | 6
Formulas:
EndDate = [StartDate]+1
EndDate = [StartDate]
StartDate = [EndDate, row above]
StartDate = [EndDate, row above]+1

## ImplementedAPIList
API Name | Region Name | Tested | Status | Implemented Date | Remarks
GetNotification | KMS Notifications | Yes | Done | 26/03/2021
GetMessageNotification | KMS Notifications | Yes | Done | 26/03/2021
MarkAsRead | KMS Notifications | Yes | Done | 26/03/2021
FetchEmployeeDetail | Reset Login Password | Yes | Done | 26/03/2021
ResetPassword | Reset Login Password | Yes | Done | 26/03/2021 | make the changes in method on controller and menthioned the changes in third sheet
FetchLogin | Reset Login Password | Yes | Done | 26/03/2021
GetUserLoginSaltKey | Change Password | Yes | Done | 30/03/2021
VerifyCredentials | Change Password | Yes | Done | 30/03/2021
ChangePassword | Change Password | Yes | Done | 30/03/2021
UnblockUser | Unblock User | Yes | Done | 31/03/2021 | make the changes in method on controller and menthioned the changes in third sheet
FetchHRMaster | SiteMaster | Yes | Done | 31/03/2021
UpdateHRMaster | SiteMaster | Yes | Done | 31/03/2021
BindDropDownViewBag | SiteMaster | Yes | Done | 31/03/2021
FetchHRMaster | PostMaster | Yes | Done | 2021-01-04
UpdateHRMaster | PostMaster | Yes | Done | 2021-01-04
BindDropDownViewBag | PostMaster | Yes | Done | 2021-01-04
FetchHRMaster | DepartmentMaster | Yes | Done | 2021-01-04
UpdateHRMaster | DepartmentMaster | Yes | Done | 2021-01-04
BindDropDownViewBag | DepartmentMaster | Yes | Done | 2021-01-04
FetchHRMaster | Division Master | Yes | Done | 2021-01-04
UpdateHRMaster | Division Master | Yes | Done | 2021-01-04
BindDropDownViewBag | Division Master | Yes | Done | 2021-01-04
SaveOBScriptMaster | ObScriptMaster | Yes | Done | 13/04/2021
GetObScriptMasterData | ObScriptMaster | Yes | Done | 2021-05-04
GetObScriptDetail | ObScriptMaster | Yes | Done | 2021-05-04
AddUpdateObScriptDetail | ObScriptMaster | Yes | Done | 2021-05-04
GetScriptType | ObScriptMaster | Yes | Done | 2021-05-04
GetPrimaryScriptbySubProcessMID | ObScriptMaster | Yes | Done | 2021-05-04
FetchEUTemplateDetail | EmployeeUpload | Yes | Done | 2021-05-04
GetEmployeeUplodedData | EmployeeUpload | Yes | Done | 2021-06-04
EmployeeDataFileUpload | EmployeeUpload | Yes | Done | 2021-06-04
EUDataExporttoExcel | EmployeeUpload | Yes | Done | 2021-06-04
GetDropDownData | Register | Yes | Done | 2021-06-04 | make the controller chnages mentioned in third sheet 8/4/2021
UpdateLogin | Register | Yes | Done | 2021-06-04 | we need to pass the loginmid and accesslmid from model not from authentication token so I make the changes in API
ListMenusForCreation | Register | Yes | Done | 2021-06-04
FetchEmployee | Register | Yes | Done | 2021-07-04
FetchLogin | Unblock User | Yes | Done | 2021-07-04
FetchEmployeeDetailRegister | Register | Yes | Done | 2021-08-04 | we need to pass the loginmid and accesslmid from model not from authentication token
BindDropDownEmployee | Auto Login Creation | Yes | Done | 2021-08-04 | we need to pass the accesslmid from model not from authentication token loginmid so I make the changes in given api
LoadNewUserLogin | Auto Login Creation | Yes | Done | 2021-08-04 | we need to pass the loginmid from model not token loginMID so I make the changes in given api
FetchMenuAccessDetailToReplicateLogin | Auto Login Creation | Yes | Done | 2021-08-04 | we will pass the loginmid in api from model not from Token LoginMID so I make the changes in given api
ReplicateNewUser | Auto Login Creation | Yes | Done | 2021-08-04
ReplicateMenu | Auto Login Creation | Yes | Done | 2021-08-04
GetMyTeam | Team Region | Yes | Done | 2021-09-04
GetMyTeamDefaultSubProcess | Team Region | Yes | Done | 2021-09-04
GetMyTeamSkills | Team Region | No | In Process | 2021-09-04
GetSubProcessTeam | Team Region | Yes | Done | 2021-09-04 | change api name into GetSubProcessTeam because GetSubProcess api already exist in subprocessMaster region
UpdateDefaultSubProcess | Team Region | Yes | Done | 2021-09-04
GetDepartmentSiteByClientMID | Team Region | Yes | Done | 2021-09-04
GetEmployeesFoMyTeamAddition | Team Region | Yes | Done | 2021-09-04
GetClients | Team Region | Yes | Done | 2021-09-04
AddEmployeesToTeam | Team Region | No | In Process | 2021-09-04
GetSkills | Team Region | No | In Process | 2021-09-04
UpdateSkill | Team Region | No | In Process | 2021-09-04
FetchSkillMasterMapping | Team Region | No | In Process | 2021-09-04
UpdateSkillMasterMapping | Team Region | No | In Process | 2021-09-04
UpdateSubProcess | Team Region | Yes | Done | 2021-09-04
ReleaseUser | Team Region | No | Done | 2021-09-04
GetSubProcess_Default | Team Region | Yes | Done | 2021-09-04
GetMyTeamDefaultScript | Team Region | Yes | Done | 2021-09-04
GetScript | Team Region | Yes | Done | 2021-09-04
UpdateDefaultScript | Team Region | Yes | Done | 2021-09-04
GetEmployeesDetailFoMyTeamAddition | Team Region | Yes | Done | 2021-09-04
BindMyTeamAdminRoles | Team Region | Yes | Done | 2021-12-04
UpdateReporting | Team Region | Yes | Done | 2021-12-04
BindReportingTo | Team Region | Yes | Done | 2021-12-04
UpdateMyTeamScript | Team Region | Yes | Done | 2021-12-04
BindMyTeamAdminUsersForSubProcessChange | Team Region | Yes | Done | 2021-12-04
ExportMyTeamAdminUsersForSubProcessChange | Team Region | Yes | Done | 2021-12-04
BindMyTeamAdminUsersForScriptChange | Team Region | Yes | Done | 2021-12-04
BindMyTeamAdminUsersForSubProcessChange | Team Region | Yes | Done | 2021-12-04
GetMyTeamUserDefaultScriptDetails | Team Region | Yes | Done | 2021-12-04
FetchMenuAccessDetail | Register Region | Yes | Done | 2021-12-04 | we will pass the loginmid in api from model not from Token LoginMID so I make the changes in given api
HREmployeeDataUpdate | Employee Data Update | Yes | Done | 13/4/2021 | created new proc proc_Admin_HRDataUpdateSearchEmployee AND proc_Admin_HREmployeeDataUpdate
GetEmployeeData | Employee Data Update | Yes | Done | 13/4/2021
GetHRSourceDataByClientID | Employee Data Update | Yes | Done | 13/4/2021 | ceated new proc proc_Admin_GetHRSourceDataByClientID AND makeproc totally dynamic query and added .DBO.HRLeaverReasons Table in DB and tabkes data has been AND inserted AND HRLeaverReasonGroups TABLE HAS BEEN ADDED AS WELL AS
LoadEmployeeDetailsForEditing | Employee Data Update | Yes | Done | 13/4/2021 | created new proc proc_Admin_GetEmployeeDetailsForEditing
HREmployeeDataUpdateLeave | Employee Data Update | Yes | Done | 13/4/2021 | CREATED NEW PROC proc_Admin_HREmployeeDataLeave AND I make some chnages in procedure

## CodeChangeInsolution
sr No | Changes Area | Changes Location | changes Reson
1 | Controller | ControllerRegister | we are returning dataset from api and we are returning that dataset in void method so we need to change all void method into dataset method so we need to return the value as dataset from void method then we will apply the bind list code after returning the data in ds from api
2 | Controller | ControllerMaster | same changes
3 | Controller | AdminControlerRegister | make the changes in UnblockUser post function and assign the Querystring.Query("MenuMDID"); in string value then assign that string value in viewBag for reolve the issue
4 | Controller | AdminControlerRegister | make the changes in UnblockUser Get function and assign the Querystring.Query("MenuMDID"); in string value then assign that string value in viewBag for reolve the issue
5 | Controller | AdminControlerRegister | make the changes in ResetPassword Post function and assign the Querystring.Query("MenuMDID"); in string value then assign that string value in viewBag for reolve the issue
6 | Controller | AdminControlerRegister | make the changes in ResetPassword Get function and assign the Querystring.Query("MenuMDID"); in string value then assign that string value in viewBag for reolve the issue

## Sheet2
Section Name | Sub Section | Page Name | API Created | Implemented Status | Reson
Home | Master | Home
Admin | Master | Ad Master
Admin | Master | Client Master
Admin | Master | Process Master
Admin | Master | Sub Process Master
Admin | Master | HR Site Master
Admin | Master | HR Division Master
Admin | Master | Department Master
Admin | Master | HR POST MASTER
Admin | Master | Script Configuration
Admin | Master(Script Config) | Tabbing Details
Admin | Master(Script Config) | Dynamic Control
Admin | Master(Script Config) | Disposition Master
Admin | Master(Script Config) | Disposition Control Mapping
Admin | Master(Script Config) | Column Master
Admin | Master(Script Config) | Additional Control Setting
Admin | Master(Script Config) | Dialler Setting
Admin | Master(Script Config) | Mail Setting
Admin | Master(Script Config) | Master Data
Admin | Master(Script Config) | External Data Columns
Admin | Master(Script Config) | Search Data Column
Admin | Master(Script Config) | Data export configuration
Admin | Master(Script Config) | Data Flow Master(DataFlowTab)
Admin | Master(Script Config) | Data Flow Master(FieldConfigurationTab)
Admin | Master(Script Config) | Data Flow Master(Scrubbing)
Admin | Master(Script Config) | Priority Users
Admin | Master(Script Config) | Collection Template Configuration
Admin | Master(Script Config) | disposition type access level Mapping
Admin | Master(Script Config) | Manual SMS SEND
Admin | Master(Script Config) | Script Dialler Portal Mapping
Admin | Master(Script Config) | Dialler user authentication Mapping
Admin | Master(Script Config) | External Search Master Data config
Admin | Master(Script Config) | User Defaul Redirect Page Master
Admin | Master(Script Config) | MiscSearchDataMaster
Admin | Master(Script Config) | WebApiConfiguration
Admin | Master(Script Config) | WebApiOutPutParaDetailMaster
Admin | Master(Script Config) | MailTemplateMiscSuboutcomeDispMapping
Admin | Master(Script Config) | SuboutcomeDependencyControlMapping
Admin | Master(Script Config) | EmailTemplateEscalationDaysSetting
Admin | Master(Script Config) | EmailTemplateVariableControlMapping
Admin | Master(Script Config) | EmailTemplateAssignFunctionParameters
Admin | Master(Script Config) | WorkingDays
Admin | Master | MultipleScripts
Admin | Master | MailBox
Admin | Master | DataFlowMaster
Admin | Master | DataFlowMaster(Field Configuration)
Admin | Master | DataFlowMaster(Scrubbing)
Admin | Master | MessageBroadCast
Admin | Master | TeamMaster
Admin | Master | TeamMailBoxMapping
Admin | Master | TeamLtwoMapping
Admin | Master | ProductBrandMaster
admin | Master | CollectionTemplate
admin | Master | DispositionMaster
admin | Master | Manual SMS SEND
admin | Master | ProductMaster
admin | Master | Core Category Master
admin | Master | Category Master
admin | Master | Type Master
admin | Master | Sub Type Master
admin | Master | Customer Complaint Report
admin | Master | DUMP REPORT
admin | Master | DRILL DOWN REPORT
admin | Master | UserBranchMapping
admin | Master | Email Template Master
admin | Master | SmsTemplateMaster
admin | Master | Collection DataAllocation
admin | User Management | Create User
admin | User Management | Update Login
admin | User Management | ResetPassword
admin | User Management | UnblockUser
admin | User Management | Sign as Different User
admin | User Management | AutoLoginCreation
admin | User Management | Auto Menu Updation
admin | User Management | Exception Menu
admin | User Management | UserDiallerMapping
admin | Manage Team | ManageTeam
admin | Upload | UploadExternalDNCData
admin | Upload | CRMDataUpload
admin | Upload | EmployeeDataUpload
admin | Upload | DataFlowBatchStatus
admin | Upload | DataFlowTablesJoin
admin | Upload | DataFlowFieldMapping
admin | Upload | DataFlowUploader
admin | Upload | DataExtraction
admin | Menu Master | MenuCreation
admin | Menu Master | ReportDetailMaster
admin | Menu Master | ReportUIDetailMaster
admin | Consolidated Report | Consolidated Report
admin | SocialMediaDashboard | SocialMediaDashboard
MyTeam | MyTeam | MyTeam
MyTeam | MyTeam | MyTeamUpdateScript
MyTeam | MyTeam | MyTeamUpdateSubProcess
MyTeam | MyTeam | MyTeamDefaultSubProcess
MyTeam | MyTeam | MyTeamDefaultScript
MyTeam | MyTeam | AddToMyTeam
MyTeam | MyTeam | AddToMyTeam
Admin | Master(Script Config) | Data Flow Master(Exclusion)
Admin | Master(Script Config) | Data Flow Master(Masterzation)