## Sheet1
Controller | Region | Owner | StartDate | EndDate | Hours | Owner | StartDate | EndDate | Hours
SharedController | Notifications | Deepshikha | 2021-03-25 | 2021-03-26 | 5 | Pawan | 2021-03-26 | 2021-03-26 | 5
AdminControllerRegister | Reset Login Password | Deepshikha | 2021-03-26 | 2021-03-26 | 5 | Pawan | 2021-03-26 | 2021-03-26 | 4
LoginController | Change Password | Deepshikha | 2021-03-30 | 2021-03-30 | 4 | Pawan | 2021-03-30 | 2021-03-30 | 9
AdminControllerRegister | Unblock User | Deepshikha | 2021-03-30 | 2021-03-30 | 3 | Pawan | 2021-03-31 | 2021-03-31 | 6
AdminControllerMaster | Site Mater | Deepshikha | 2021-03-31 | 2021-03-31 | 4 | Pawan | 2021-03-31 | 2021-03-31 | 3
AdminControllerMaster | Department Mater | Deepshikha | 2021-04-01 | 2021-04-01 | 4 | Pawan | 2021-04-01 | 2021-04-01 | 3
AdminControllerMaster | Division Mater | Deepshikha | 2021-04-01 | 2021-04-01 | 4 | Pawan | 2021-04-01 | 2021-04-01 | 3
AdminControllerMaster | Post Master | Deepshikha | 2021-04-01 | 2021-04-01 | 6 | Pawan | 2021-04-01 | 2021-04-01 | 3
UploadController | EmployeeUpload | Deepshikha | 2021-04-01 | 2021-04-06 | 6 | Pawan | 2021-04-05 | 2021-04-06 | 9
AdminControllerRegister | Register - Create User | Deepshikha | 2021-04-06 | 2021-04-06 | 6 | Pawan | 2021-04-06 | 2021-04-06 | 9
AdminControllerRegister | Register - Update User | Deepshikha | 2021-04-07 | 2021-04-07 | 6 | Pawan | 2021-04-07 | 2021-04-07 | 9
AdminController | Auto Login Creation | Deepshikha | 2021-04-07 | 2021-04-08 | 6 | Pawan | 2021-04-08 | 2021-04-08 | 9
TeamController | Team Master | Deepshikha | 2021-04-08 | 2021-04-09 | 6 | Pawan | 2021-04-09 | 2021-04-12 | 9
AdminController | Employee Data Update | Deepshikha | 2021-04-09 | 2021-04-12 | 6 | Pawan | 2021-04-13 | 2021-04-13 | 9
LoginController | Login Creation | Deepshikha | 2021-04-12 | 2021-04-13 | 7 | Pawan | 2021-04-14 | 2021-04-14 | 5
LoginController | Login Page - Forgot Password | Deepshikha | 2021-04-14 | 2021-04-14 | 5 | Pawan | 2021-04-14 | 2021-04-14 | 4
LoginController | Login Page - Password Expired | Deepshikha | 2021-04-14 | 2021-04-15 | 5 | Pawan | 2021-04-15 | 2021-04-15 | 5
LoginController | My Role Assignment | Deepshikha | 2021-04-15 | 2021-04-15 | 5 | Pawan | 2021-04-15 | 2021-04-15 | 4
LoginController | Update Profile | Deepshikha | 2021-04-16 | 2021-04-16 | 6 | Pawan | 2021-04-16 | 2021-04-16 | 9
LoginController | Change Reset Password Link | Deepshikha | 2021-04-19 | 2021-04-19 | 6 | Pawan | 2021-04-19 | 2021-04-19 | 9
LoginController | Login Page - OTP | Deepshikha | 2021-04-20 | 2021-04-20 | 6 | Pawan | 2021-04-20 | 2021-04-21 | 9
"
"
"
"
Formulas:
EndDate = [StartDate]+1
EndDate = [EndDate]
StartDate = [EndDate]
StartDate = [EndDate, row above]