## API Task TimeTable
Sr.No | Region | Owner | Hour | StartDate | EndDate
1 | Manage KnowleadgeBase Region | Deepshikha | 6 | 2021-02-25 | 2021-02-26
2 | Update Knowleadgebase Region | Deepshikha | 4 | 2021-02-26 | 2021-02-26
3 | View Knowleadgebase Region | Deepshikha | 4 | 2021-03-01 | 2021-03-01
4 | Snippet Spectrum Region | Deepshikha | 4 | 2021-03-01 | 2021-03-02
5 | Update Descision tree region | Deepshikha | 5 | 2021-03-02 | 2021-03-02
6 | Decision Tree Region | Deepshikha | 5 | 2021-03-03 | 2021-03-03
7 | Article Master Region | Deepshikha | 4 | 2021-03-03 | 2021-03-04
8 | Category Master | Deepshikha | 4 | 2021-03-04 | 2021-03-05
9 | Sub Category Master Region | Deepshikha | 4 | 2021-03-05 | 2021-03-05
10 | FAQ Admin | Deepshikha | 4 | 2021-03-08 | 2021-03-08
11 | Knowleadgebase, Category, Sub Category,Article | Mayank | 5 | 2021-02-26 | 2021-03-01
12 | Faq Agent | Mayank | 4 | 2021-03-01 | 2021-03-01
13 | Knowleadgebase Action Version View | Mayank | 4 | 2021-03-02 | 2021-03-02
14 | Knowleadgebase Home | Mayank | 4 | 2021-03-02 | 2021-03-03
15 | Bind the Grid According to Status | Mayank | 4 | 2021-03-03 | 2021-03-03
16 | Bind Latest Comments | Mayank | 4 | 2021-03-04 | 2021-03-04
17 | Knowleadgebase Maker | Mayank | 5 | 2021-03-04 | 2021-03-05
18 | Knowleadgebase Reviewer | Mayank | 5 | 2021-03-05 | 2021-03-08
19 | Knowleadgebase Approvar | Mayank | 4 | 2021-03-08 | 2021-03-08
20 | Category Approvar | Mayank | 4 | 2021-03-09 | 2021-03-09
21 | KBRealease Page Functionality | Mayank | 4 | 2021-03-09 | 2021-03-10
22 | Delete and Load KB Data | Mayank | 4 | 2021-03-10 | 2021-03-10
1 | Manage KnowleadgeBase Region | Pawan | 3 | 2021-03-01 | 2021-03-01
2 | Update Knowleadgebase Region | Pawan | 3 | 2021-03-01 | 2021-03-01
3 | View Knowleadgebase Region | Pawan | 3 | 2021-03-02 | 2021-03-02
4 | Snippet Spectrum Region | Pawan | 1 | 2021-03-02 | 2021-03-02
5 | Update Descision tree region | Pawan | 2 | 2021-03-02 | 2021-03-02
6 | Decision Tree Region | Pawan | 4 | 2021-03-03 | 2021-03-03
7 | Article Master Region | Pawan | 2 | 2021-03-03 | 2021-03-03
8 | Category Master | Pawan | 4 | 2021-03-03 | 2021-03-04
9 | Sub Category Master Region | Pawan | 2 | 2021-03-04 | 2021-03-04
10 | Knowleadgebase, Category, Sub Category,Article | Pawan | 3 | 2021-03-05 | 2021-03-05
11 | Faq Agent | Pawan | 3 | 2021-03-05 | 2021-03-05
12 | FAQ Admin | Pawan | 3 | 2021-03-08 | 2021-03-08
13 | Knowleadgebase Action Version View | Pawan | 3 | 2021-03-08 | 2021-03-08 | Pending
14 | Knowleadgebase Home | Pawan | 2 | Tuesday,9 March 2021 | Tuesday,9 March 2021
15 | Bind the Grid According to Status | Pawan | 2 | Tuesday,9 March 2021 | Tuesday,9 March 2021
16 | Bind Latest Comments | Pawan | 2 | Tuesday,9 March 2021 | Tuesday,9 March 2021
17 | Knowleadgebase Maker | Pawan | 6 | 2021-03-10 | 2021-03-10
18 | Knowleadgebase Reviewer | Pawan | 3 | 2021-03-12 | 2021-03-12
19 | Knowleadgebase Approvar | Pawan | 3 | 2021-03-12 | 2021-03-12
20 | Category Approvar | Pawan | 3 | 2021-03-15 | 2021-03-15
21 | KBRealease Page Functionality | Pawan | 3 | 2021-03-15 | 2021-03-15
22 | Delete and Load KB Data | Pawan | 6 | Wednesday,17 March 2021 | Wednesday,17 March 2021
Formulas:
EndDate = [StartDate]+1
EndDate = [StartDate]
StartDate = [EndDate, row above]
StartDate = [EndDate, row above]+3

## Implemented API
Sr No | API Name | With Token Tested | Status
1 | GetSaveUpdateKnowledgeBase_Attachment | Yes | Ok
2 | GetSaveUpdateKnowledgeBase_Detail | Yes | Ok
3 | KnowledgeBase_Detail_Edit | Yes | Ok
4 | KnowledgeBase_Detail_View | Yes | Ok
5 | proc_KnowledgeBase_CheckIsarticleRated | Yes | Ok
6 | BindDropDown4 | Yes | Ok
7 | GetClients | Yes | Ok
8 | GetArticle | Yes | Ok
9 | SaveArticleData | Yes | Ok
10 | GetCategory | Yes | Ok
11 | SaveCategoryData | Yes | Ok
12 | GetSubCategorybyCategoryMID | Yes | Ok
13 | GetArticlebyClientMID | Yes | Ok
14 | ShowKnowledgeBaseFAQ | Yes | Ok
15 | Save_AcessDetails | Yes | Not OK
16 | GetKnowledgeBaseFAQ | Yes | Ok
17 | KnowledgeBase_GetParentNode | No | Pending compilation error
18 | KnowledgeBase_DeleteNode | No | Useless Api should be DeleteNodeDetail
19 | KnowledgeBase_DetailDecisionTree_View | Yes | Ok
20 | proc_KnowledgeBase_Insertanylaysis | No | Not Need To implement
21 | KnowledgeBase_Detail_Feedback | Yes | Ok
22 | KnowledgeBase_Detail_View | Yes | Ok
23 | FetchNode | Yes | Ok
24 | GetSaveUpdateKnowledgeBase_1_Data | Yes | Ok
25 | GetSearchDataclient | Yes | Ok
26 | GetSearchData | Yes | Ok
27 | SaveKnowledgeBaseTreeView | Yes | Ok
28 | GetSubCategory | Yes | Ok
29 | SaveSubCategoryData | Yes | Ok
30 | GetCategorybyClientMID | Yes | Ok
31 | SaveKnowledgeBaseFAQ | Yes | Ok
32 | BindFAQType | Yes | Already Inbuild in Binddropdown4 Api
33 | SearchKnowledgeBaseFromHome | No | Function Not In use not need to Implement
34 | SearchFAQFromHome | Yes | Ok
35 | SearchFAQFromHomeNotification | No | Function call from notification only so we will not implement
36 | SearchKnowledgeBaseFAQ | Yes | Ok
37 | BindDataWithCondition | Yes | Ok
38 | BindDataWithConditionReviewers | Yes | Ok
39 | BindDataAccordingtoConditionApproverCase | Yes | Ok
40 | KnowledgeBaseBindLatestComment | Yes | Ok
41 | DeleteKnowledgeBaseFAQ | Yes | Ok
42 | GetSearchDataMaker | Yes | Ok | Data properly not showing working
43 | SaveUpdateKnowledgeBaseData | Yes | Ok
44 | KnowledgeBaseUniqueCheck | Yes | Ok
45 | KnowledgeBaseUpdateStatusByMaker | Yes | Ok
46 | GetSearchDataSentForApproval | Yes | Ok
47 | UpdateStatusByMaker_again | No | This Function is not using
48 | LoadAllHistory | Yes | Ok
49 | ShowPendingFromViewersHand | Yes | Ok
50 | UpdateStatusByReviewers | Yes | Ok
51 | ViewActionTakenByReviewers | Yes | Ok
52 | BindDynamicStatus | Yes | Ok
53 | ShowPendingFromApproverHand | Yes | Ok
54 | ViewActionTakenByApprovar | Yes | Ok
55 | CategoryListForApproval | Yes | Ok | Logout issue is going on need to check
56 | SubCategoryListForApproval | Yes | Ok
57 | UpdateCategoryForApproval | Yes | Ok
58 | GetSearchDataRelease | Yes | Ok
59 | ReleaseKnowledgeBaseData | Yes | Ok
60 | DeleteKnowledgeBase | Yes | Ok
61 | LoadAllAveradgeRating | Yes | Ok
62 | LoadallNodeHitsTop15 | Yes | Ok
63 | GetSearchDataKnowledgeBaseVersionCopy | Yes | Ok | Dta is Shwoing
64 | KnowledgeBaseDecisionTreeVersionCopyView | Yes | Ok | Dta is Shwoing
65 | KnowledgeBaseCheckVersionCopy | Yes | Not Ok | procedure not available
66 | KnowledgeBaseDetailViewVersionCopy
Master API
67 | GetClientData | Yes | Ok
68 | SaveClient | Yes | Ok
69 | GetClientsDataforAcitivity | Yes | Ok
70 | GetActiveClientsData | Yes | Ok
71 | GetProcessData | Yes | Ok
72 | SaveProcess | Yes | Ok
73 | GetProcessbyClientMID | Yes | Ok
74 | GetSubProcessData | Yes | Ok
75 | GetSubProcessData | Yes | Ok
76
77 | GetMessage | Yes | Ok
78 | MessageBroadCast | Yes | Ok
79 | BindMessageClientList | Yes | Ok
80 | BindScriptList | Yes | Ok
81 | BindMessageType | Yes | Ok
82 | SaveMessageBroadCast | Yes | Ok
83 | DeleteProcessUpdate | No
84 | DeleteBroadcastMessage | No