## API Task TimeTable
Sr.No | Region | Owner | Hour | StartDate | EndDate
1 | Manage KnowleadgeBase Region | Deepshikha | 6 | 2021-02-25 | 2021-02-26
2 | Update Knowleadgebase Region | Deepshikha | 4 | 2021-02-26 | 2021-02-26
3 | View Knowleadgebase Region | Deepshikha | 4 | 2021-03-01 | 2021-03-01
4 | Snippet Spectrum Region | Deepshikha | 4 | 2021-03-01 | 2021-03-02
5 | Update Descision tree region | Deepshikha | 5 | 2021-03-02 | 2021-03-02
6 | Decision Tree Region | Deepshikha | 5 | 2021-03-03 | 2021-03-03
7 | Article Master Region | Deepshikha | 4 | 2021-03-03 | 2021-03-04
8 | Category Master | Deepshikha | 4 | 2021-03-04 | 2021-03-05
9 | Sub Category Master Region | Deepshikha | 4 | 2021-03-05 | 2021-03-05
10 | FAQ Admin | Deepshikha | 4 | 2021-03-08 | 2021-03-08
11 | Knowleadgebase, Category, Sub Category,Article | Mayank | 5 | 2021-02-26 | 2021-03-01
12 | Faq Agent | Mayank | 4 | 2021-03-01 | 2021-03-01
13 | Knowleadgebase Action Version View | Mayank | 4 | 2021-03-02 | 2021-03-02
14 | Knowleadgebase Home | Mayank | 4 | 2021-03-02 | 2021-03-03
15 | Bind the Grid According to Status | Mayank | 4 | 2021-03-03 | 2021-03-03
16 | Bind Latest Comments | Mayank | 4 | 2021-03-04 | 2021-03-04
17 | Knowleadgebase Maker | Mayank | 5 | 2021-03-04 | 2021-03-05
18 | Knowleadgebase Reviewer | Mayank | 5 | 2021-03-05 | 2021-03-08
19 | Knowleadgebase Approvar | Mayank | 4 | 2021-03-08 | 2021-03-08
20 | Category Approvar | Mayank | 4 | 2021-03-09 | 2021-03-09
21 | KBRealease Page Functionality | Mayank | 4 | 2021-03-09 | 2021-03-10
22 | Delete and Load KB Data | Mayank | 4 | 2021-03-10 | 2021-03-10
1 | Manage KnowleadgeBase Region | Pawan | 3 | 2021-03-01 | 2021-03-01
2 | Update Knowleadgebase Region | Pawan | 3 | 2021-03-01 | 2021-03-01
3 | View Knowleadgebase Region | Pawan | 3 | 2021-03-02 | 2021-03-02
4 | Snippet Spectrum Region | Pawan | 1 | 2021-03-02 | 2021-03-02
5 | Update Descision tree region | Pawan | 2 | 2021-03-02 | 2021-03-02
6 | Decision Tree Region | Pawan | 4 | 2021-03-03 | 2021-03-03
7 | Article Master Region | Pawan | 2 | 2021-03-03 | 2021-03-03
8 | Category Master | Pawan | 4 | 2021-03-03 | 2021-03-04
9 | Sub Category Master Region | Pawan | 2 | 2021-03-04 | 2021-03-04
10 | Knowleadgebase, Category, Sub Category,Article | Pawan | 3 | 2021-03-05 | 2021-03-05
11 | Faq Agent | Pawan | 3 | 2021-03-05 | 2021-03-05
12 | FAQ Admin | Pawan | 3 | 2021-03-08 | 2021-03-08
13 | Knowleadgebase Action Version View | Pawan | 3 | 2021-03-08 | 2021-03-08
14 | Knowleadgebase Home | Pawan | 2 | Tuesday,9 March 2021 | Tuesday,9 March 2021
15 | Bind the Grid According to Status | Pawan | 2 | Tuesday,9 March 2021 | Tuesday,9 March 2021
16 | Bind Latest Comments | Pawan | 2 | Tuesday,9 March 2021 | Tuesday,9 March 2021
17 | Knowleadgebase Maker | Pawan | 6 | 2021-03-10 | 2021-03-10
18 | Knowleadgebase Reviewer | Pawan | 3 | 2021-03-12 | 2021-03-12
19 | Knowleadgebase Approvar | Pawan | 3 | 2021-03-12 | 2021-03-12
20 | Category Approvar | Pawan | 3 | 2021-03-15 | 2021-03-15
21 | KBRealease Page Functionality | Pawan | 3 | 2021-03-15 | 2021-03-15
22 | Delete and Load KB Data | Pawan | 6 | Wednesday,17 March 2021 | Wednesday,17 March 2021
Formulas:
EndDate = [StartDate]+1
EndDate = [StartDate]
StartDate = [EndDate, row above]
StartDate = [EndDate, row above]+3

## Implemented API
Sr No | API Name | Region | With Token Tested | Status
1 | GetSaveUpdateKnowledgeBase_Attachment | Update KnowledgeBase | Yes | Ok
2 | GetSaveUpdateKnowledgeBase_Detail | Update KnowledgeBase | Yes | Ok
3 | KnowledgeBase_Detail_Edit | Manage KnowledgeBase | Yes | Ok
4 | KnowledgeBase_Detail_View | Update KnowledgeBase | No | Pending
5 | proc_KnowledgeBase_CheckIsarticleRated | DecisionTree | No | Pending
6 | BindDropDown4 | Update DecisionTree | Yes | Ok
7 | GetClients | Article Master | Yes | Ok
8 | GetArticle | Article Master | Yes | Ok
9 | SaveArticleData | Article Master | Yes | Ok
10 | GetCategory | Category Master | Yes | Ok
11 | SaveCategoryData | Category Master | Yes | Ok
12 | GetSubCategorybyCategoryMID | KnowledgeBase Category, SubCategory, Article Enhancement Part | Yes | Ok
13 | GetArticlebyClientMID | KnowledgeBase Category, SubCategory, Article Enhancement Part | Yes | Ok
14 | ShowKnowledgeBaseFAQ | FAQ Agent | Yes | Ok
15 | Save_AcessDetails | FAQ Agent | No | Pending
16 | GetKnowledgeBaseFAQ | FAQ Agent | Yes | Ok
17 | KnowledgeBase_GetParentNode | DecisionTree | No | Pending
18 | KnowledgeBase_DeleteNode | DecisionTree | No | Useless Api should be DeleteNodeDetail
19 | KnowledgeBase_DetailDecisionTree_View | DecisionTree | No | Pending
20 | proc_KnowledgeBase_Insertanylaysis | View KnowledgeBase | No | Not Need To implement
21 | KnowledgeBase_Detail_Feedback | View KnowledgeBase | No | Pending
22 | KnowledgeBase_Detail_View | Update KnowledgeBase | No | Pending
23 | FetchNode | Update KnowledgeBase | Yes | Ok
24 | GetSaveUpdateKnowledgeBase_1_Data | Manage KnowledgeBase | Yes | Ok
25 | GetSearchDataclient | Manage KnowledgeBase | Yes | Ok
26 | GetSearchData | Manage KnowledgeBase | Yes | Ok
27 | SaveKnowledgeBaseTreeView | Update DecisionTree | No | Pending
28 | GetSubCategory | Sub Category Master | Yes | Ok
29 | SaveSubCategoryData | Sub Category Master | Yes | Ok
30 | GetCategorybyClientMID | Sub Category Master | Yes | Ok
31 | SaveKnowledgeBaseFAQ | KnowledgeBase FAQ | Yes | Ok
32 | BindFAQType | KnowledgeBase FAQ | Yes | Already Inbuild in Binddropdown4 Api
33 | SearchKnowledgeBaseFromHome | KnowledgeBase Home | No | Function Not In use not need to Implement
34 | SearchFAQFromHome | KnowledgeBase Home | Yes | Ok
35 | SearchFAQFromHomeNotification | KnowledgeBase Home | No | Function call from notification only so we will not implement
36 | SearchKnowledgeBaseFAQ | KnowledgeBase Home | No | Data is not showing (Pending)
37 | BindDataWithCondition | BIND THE GRID ACCORDING TO STATUS | Yes | Ok
38 | BindDataWithConditionReviewers | Reviewer Region | Yes | Ok
39 | BindDataAccordingtoConditionApproverCase | Approver Region | Yes | Ok
40 | KnowledgeBaseBindLatestComment | Bind Latest Comments | Yes | Ok
41 | DeleteKnowledgeBaseFAQ | KnowledgeBase FAQ | No | Pending some issue is going on
42 | GetSearchDataMaker | Maker Region | Yes | Ok | Data properly not showing working
43 | SaveUpdateKnowledgeBaseData | Maker Region | Yes | Ok
44 | KnowledgeBaseUniqueCheck | Maker Region | Yes | Ok
45 | KnowledgeBaseUpdateStatusByMaker | Maker Region | Yes | Ok
46 | GetSearchDataSentForApproval | Maker Region | Yes | Ok
47 | UpdateStatusByMaker_again | Maker Region | No | This Function is not using
48 | LoadAllHistory | Maker Region | Yes | Ok
49 | ShowPendingFromViewersHand | Reviewer Region | Yes | Ok
50 | UpdateStatusByReviewers | Reviewer Region | Yes | Ok
51 | ViewActionTakenByReviewers | Reviewer Region | Yes | Ok
52 | BindDynamicStatus | Reviewer Region | Yes | Ok
53 | ShowPendingFromApproverHand | Approver Region | Yes | Ok
54 | ViewActionTakenByApprovar | Approver Region | Yes | Ok