## Sheet1
Login Type | SuperAdmin | Admin Module
Password: | Welcome@1234567
Testing URL | https://tpapps.teleperformancedibs.com/KmsUnifiedCRM/
Section Name | SubSectionName | Page Name | Check Functionality |  | LoginType | Issue If any | Final Status | Round 2 Status (30/04/2021)
Admin | Master | ClientMaster | Save,Edit |  | SuperAdmin |  | Ok
Admin | Master | ProcessMaster | Save,Edit |  | SuperAdmin |  | Ok
Admin | Master | Sub Process Master | Save,Edit |  | SuperAdmin |  | Ok
Admin | Master | Hr Site Master | Save,Edit |  | SuperAdmin |  | Ok
Admin | Master | Hr devision Master | Save,Edit |  | SuperAdmin |  | Ok
Admin | Master | Department Master | Save,Edit |  | SuperAdmin |  | Ok
Admin | Master | Hr PostMaster | Save,Edit |  | SuperAdmin |  | Ok
Admin | Master | Script Configuration | Save,Edit,Search |  | SuperAdmin |  | Ok
Admin | User Management | Create User | Save and Update and Bind All Drodpwn |  | SuperAdmin |  | Ok
Admin | User Management | UpdateLogin | Update the Login Successfully |  | SuperAdmin | xml file is updating as like superadmin menu for all accesslmid due to passing token LoginMID | Not Ok(Issue) | Fixed
Admin | User Management | ResetPassword | Password is Reseting as Welcome@123 |  | SuperAdmin |  | Ok
Admin | User Management | UnblockUser | User is Unblocking Successfully |  | SuperAdmin |  | Ok
Admin | User Management | AutoLoginCreation | User is replicate Sucessfully |  | SuperAdmin |  | Ok
Admin | User Management | Auto Menu Updation | Menu is Updating and selected users menu is showing when click on view menu button |  | SuperAdmin |  | Ok
Admin | Upload | Employee Data Upload | Data is uploading Sucessfully |  | SuperAdmin |  | Ok
Admin | Master | Employee Update | Employee is updating |  | SuperAdmin |  | Ok
Admin | Master | Employee Regisnation | Edit is Working Fine |  | SuperAdmin |  | Ok
My Team | My Team | MyTeam | Working |  | SuperAdmin |  | Ok
My Team | My Team | MyTeamUpdateScript | Script is updating |  | SuperAdmin |  | Ok
My Team | My Team | MyTeamUpdateSubProcess | Sub process is Updating |  | SuperAdmin |  | Ok
My Team | My Team | MyTeamDefaultSubProcess | Default Sub process is Updating |  | SuperAdmin |  | Ok
My Team | My Team | MyTeamDefaultScript | Default script is updating |  | SuperAdmin |  | Ok
My Team | My Team | AddToMyTeam | Problem Performing Error |  | SuperAdmin |  | Not Ok(Issue) | Fixed
Admin | Manage Team | Manage Team | Data is not showing and count is showing |  | SuperAdmin |  | Not Ok(Issue) | Fixed
Admin | User Management | Update Temparory assword | password is not updating when new user do login whi his temp password |  | SuperAdmin |  | Not Ok(Issue) | Fixed
Login Type | Agent(Advisor) | KMS Module
Password: | Welcome@1234567
Testing URL | https://tpapps.teleperformancedibs.com/KmsUnifiedCRM/
KnowledgeBase | KnowledgeBase | Manage Knowledgebase | 1) View Approved FAQ is working 2) view Knowledgege all detail 3) Create Version:Version is creating |  | Agent(Advisor) |  | Ok
KnowledgeBase | KnowledgeBase | KnowledgeBaseMaker | 1) Edit is working 2) new Node is saving 3) Node is updating 4) F&Q is adding and updating and deleting and faq is searching 5) File is adding when add new Faq only excel file format is chcked 6) Paging is Working in draft Tab 7) View Button is Working Draft Tab 8) View History is Working Fine 9) sent to reviewer button is working and article is showing in send to reviewer Tab 10) Notification is working and Data is showing 11) KB IS deleting Successfully 12) Returned Article by reviewer or approver is showing 13) Add New KB Adding only spectrum tested |  | Agent(Advisor) | when add new faq after add the faq the end date text box is blank that should be seen as selected of expiry date of KB | ok
KnowledgeBase | KnowledgeBase | Index Page | 1) Decision graphycal View is Ceating 2) Agent is able to view the KB
KnowledgeBase | KnowledgeBase | KnowledgeBaseHome | 1) Top 15 KB Hits and Article is binding 2) Notification is binding 3) search is working from home page and redirecting to index page if we are serach KB and if we are searching PU its redirecting to Messagebrodcast Page |  | Agent(Advisor) |  | Ok
KnowledgeBase | KnowledgeBase | Article | Save ,edit |  | Agent(Advisor) |  | Ok
KnowledgeBase | KnowledgeBase | Category Master | Save ,edit |  | Agent(Advisor) |  | Ok
KnowledgeBase | KnowledgeBase | Subcategory Master | Save ,edit |  | Agent(Advisor) |  | Ok
KnowledgeBase | KnowledgeBase | KnowledgeBase Version | Not testted |  | Agent(Advisor) |  | Page Access is not available
KnowledgeBase | KnowledgeBase | KnowledgeBaseFAQ | Save ,edit ,delete are working fine |  | Agent(Advisor) |  | Ok
Admin | Password | UpdatePassword(from top menu) | password is updating and login new password successfully |  | Agent(Advisor) |  | Ok
Admin | Update Profile | UpdateProfile(from top menu) | Password is not taking more than 15 character |  | Agent(Advisor) |  | Not Ok
Admin | MyRole Assigment | MyRoleAssignment | Not Working |  | Agent(Advisor) |  | Not Ok | Fixed
Login Type | TL(Reviewer) | KMS Module
Password: | Welcome@1234567
Testing URL | https://tpapps.teleperformancedibs.com/KmsUnifiedCRM/
KnowledgeBase | KnowledgeBase | KnowledgeBaseReviewer | 1) article is showing which has been sent by advisor for review in pending for review tab 2) Rewer is able to return and approve the article 3) after approve the article it is showing in actioned tab in colour 4) Load History is working |  | TL (Reviewer) |  | Ok
KnowledgeBase | KnowledgeBase | Manage Knowledgebase | 1) View Approved FAQ is working 2) view Knowledgege all detail 3) Create Version:Tested |  | TL (Reviewer) |  | Ok
KnowledgeBase | KnowledgeBase | Index Page | 1) Decision graphycal View is Ceating 2) Agent is able to view the KB |  | TL (Reviewer) |  | Ok
KnowledgeBase | KnowledgeBase | KnowledgeBaseHome | 1) Top 15 KB Hits and Article is binding 2) Notification is binding 3) search is working from home page and redirecting to index page if we are serach KB and if we are searching PU its redirecting to Messagebrodcast Page |  | TL (Reviewer) |  | Ok
KnowledgeBase | KnowledgeBase | KnowledgeBase Version | Search is working and view is working and old version data is showing but faq is not binding jquery error is showing |  | TM (Approver) |  | Pending | Fixed
KnowledgeBase | KnowledgeBase | KnowledgeBaseFAQ | Save ,edit ,delete are working fine |  | TL (Reviewer) |  | Ok
KnowledgeBase | KnowledgeBase | KnowledgeBaseMaker | Not tested with creating New KB By TL |  | TL (Reviewer) |  | No Permission
Admin | Password | UpdatePassword(from top menu) | password is updating and login new password successfully |  | TL (Reviewer) |  | Ok
Admin | Update Profile | UpdateProfile(from top menu) | Password is not taking more than 15 character |  | TL (Reviewer) |  | Not Ok | Fixed
Admin | MyRole Assigment | MyRoleAssignment | Not Working |  | TL (Reviewer) |  | Not Ok | Fixed
Login Type | TM(Approver) | KMS Module
Password: | Welcome@1234567
Testing URL | https://tpapps.teleperformancedibs.com/KmsUnifiedCRM/
KnowledgeBase | KnowledgeBase | KnowledgeBase Version | Search is working and view is working and old version data is showing but faq is not binding jquery error is showing |  | TM (Approver) |  | Pending | Fixed
KnowledgeBase | KnowledgeBase | KnowledgeBaseFAQ | Save ,edit ,delete are working fine |  | TM (Approver) |  | Ok
KnowledgeBase | KnowledgeBase | KnowledgeBaseMaker | Not tested with creating New KB By TM |  | TM (Approver) |  | Ok
KnowledgeBase | KnowledgeBase | KnowledgeBaseHome | 1) Top 15 KB Hits and Article is binding 2) Notification is binding 3) search is working from home page and redirecting to index page if we are serach KB and if we are searching PU its redirecting to Messagebrodcast Page |  | TM (Approver) |  | Ok
KnowledgeBase | KnowledgeBase | KnowledgeBaseApproval | 1) artcile is showing which has been sent by reviewer for approve: working 2) artcile is approving and showing in second tab (actioned tab as approved) 3) Load History working |  | TM (Approver) |  | Ok
Admin | Master | MessageBroadCast | 1) Message Broadcast is saving 2) File is uploading 3) Edit is working Fine 4) Delete is working File 5) |  | TM (Approver) |  | Ok
KnowledgeBase | KnowledgeBase | KnowledgeBaseFAQ | Save ,edit ,delete are working fine |  | TM (Approver) |  | Ok
Master | Reports | Reports | Not tested |  | TM (Approver) |  | Ok
KnowledgeBase | KnowledgeBase | Category and Subcategory Approver | all Category and Subcatetory is Approving |  | TM (Approver) |  | Ok
KnowledgeBase | KnowledgeBase | Knowledgebase Release Page | Knowledgebase is searching |  | TM (Approver) |  | Ok
KnowledgeBase | KnowledgeBase | Manage Knowledgebase | 1) View Approved FAQ is working 2) view Knowledgege all detail 3) Create Version:Tested |  | TM (Approver) |  | Ok
Admin | Password | UpdatePassword(from top menu) | password is updating and login new password successfully |  | TM (Approver) |  | Ok
Admin | Update Profile | UpdateProfile(from top menu) | Password is not taking more than 15 character |  | TM (Approver) |  | Not Ok | Fixed
Admin | MyRole Assigment | MyRoleAssignment | Not Working |  | TM (Approver) |  | Not Ok | Fixed
Note :This is all testing scenerio for spectrum only after the complete of spectrum testing will start the testing for Decision Tree module
Decision Tree Module Testing
Agent Login
Add KB(article) | working
Add KB NODE | working | Need to fix some design issue and js issue | [5 empty] | Fixed
FAQ | Not working | faq is saving and updating but date is showing as undefined in text box tested xlsx,png,pdf,docs,pptx,MP4 | [5 empty] | Fixed
view the Added KB IN DRAFT TAB | Not working | The entered file type is invalid alert is showing need to chck in jquery | [5 empty] | Fixed
Bind Faq according nodes | working | need to fix only design issue file for download is not showing properly but file is downloading
Reviewer Login
sent item by maker for review | Showing in tab | Working
view the KB (Decision tree) | Not working | The entered file type is invalid alert is showing need to chck in jquery
Remaining functinality has been checked
Approver (TM) Login
ITEM IS showing sent by reviewer | Showing in tab | Working
view the KB (Decision tree) | Not working | The entered file type is invalid alert is showing need to chck in jquery |  |  |  | Ok
Remaining functinality has been checked
approved KB BY TM | Working
Overall Issue Fnding which we have to need the fix on asap
Updatting the XML According to search user name in demoadmin |  |  | Admin Module | Code Issue |  |  |  | Fixed
Role Assignment issue |  |  | Admin Module | Code Issue |  |  |  | Fixed
Fix the Design issue for adding the Kb node for decision tree |  |  | KMS Module | Design and jquery validation issues |  |  |  | Fixed
fix the issue in knowledgebase version when faq is not binding according to node |  |  | KMS Module | Jquery Issue |  |  |  | Fixed
Reset the new user Temparory Password when he do login |  |  | Login Module | Code Issue |  |  |  | Fixed
Update Profile issue by user |  |  | Admin Module | vaidation issue |  |  |  | Fixed
Faq Page issue end date should be seen always as selected KB expirydate |  |  | KMS Module | Jquery Issue |  |  |  | Fixed
Manage team Issue data is not showing but count is shwoing |  |  | Team Module | Code Issue/Jquery Issue/sql issue |  |  |  | Fixed